# Urban tree canopy cooling deliverables schedule

Version 6.2  |  Pilot first and expansion after review  |  19 September 2026

# Current assignment

Complete the amended v6.2 pilot and bring it to review before any full-city scaling. This schedule is ordered by dependencies; no new calendar deadlines are invented. The meeting and later email contain scheduling suggestions, but no meeting is scheduled by these documents.

# First audit the inputs

Check full ECOSTRESS mission metadata, pagination and distinct city-pass identities, then apply the study window. Audit tile overlap, duplicate ground cells and area-weighted raster aggregation. Verify the data path, product collections, wideband emissivity and QA.

Done means a reproducible count/overlap ledger and known-case aggregation checks, without reading sealed estimates.

# Then freeze the two-city sample and decisions

Keep the five frozen Phoenix passes. Select Atlanta or Charlotte and five equivalent passes on nonthermal canopy heterogeneity and afternoon coverage. Confirm wider within-block canopy support before thermal download.

Freeze pass-level Sxx/Bvar minima from observed nonthermal distributions; define the city precision rule, canopy pair, references, late-time target, scale tolerance, zero convention, simulation scenarios and time/power specification before fitting or coefficient access. A short decision-log entry with source hashes is sufficient.

# Build and run the limited pilot

Implement block intercepts plus a pooled city-pass slope in both LST and M. Verify units, matched samples, block bootstrap, prediction centering, exact fourth-root conversion, registration and sealed output behavior.

Run five Phoenix and five selected higher-canopy passes. Report open precision/support diagnostics and keep point estimates sealed. Run labeled synthetic mixing tests in the separate synthetic root. A brief high-resolution canopy check is optional validation and must not delay the main work.

# Review precision and then measurement scale

Use the frozen interpretation of the approximately 0.10 K per 10 percentage points SE benchmark. Either-city success supports review; both-city failure requires reporting the numbers and stopping dependent work.

After freeze, a precision ruling and recorded release, inspect the pass plot and evaluate the prespecified 10:30-to-late-afternoon contrasts for the total-time and secondary geometry/season-standardized patterns. Compare LST and temperature-equivalent M results against the prospectively frozen tolerance. Missing time support or ambiguous precision remains unresolved, not a pass.

# Expansion only after review

Following a recorded pilot-review decision, process the available Phoenix and Los Angeles passes and then consider eight to twelve additional cities. Choose them on canopy heterogeneity and clear-sky afternoon coverage before thermal download. Determine pass requirements through simulation/power.

Keep VPD descriptive, HLS/SWIR research deferred and eight-class unmixing out of scope. Maintain the short literature note, decision log, manifests, output isolation and sealing. New conformance and per-deliverable packages are set aside.