# Deliverables Schedule:

## What is produced at each step, in what form, and where it lands in the paper

This document accompanies Step-by-Step Guide For every step in that guide it names the artifact to be produced, the form it takes, what it must contain, and which part of the manuscript it eventually feeds. Deliverable identifiers follow the step numbers, so D1b is the product of Step 1b.

Nothing here changes the analysis. It fixes what gets handed over and what gets reviewed, so that a step is either complete or it is not.

## 1. What counts as a submitted deliverable

Each deliverable is one dated folder:

D<step>_<shortname>_v6_2_YYYYMMDD/
  memo.pdf              two pages maximum
  figures/              .png at 300 dpi, plus the source .pdf or .svg
  tables/               .csv, one file per table, with a header row
  data/                 the output dataset, or a pointer file if it is large
  code_commit.txt       repository commit hash and the exact command run
  checksums.txt         checksums for every file in the folder

Four rules govern the contents.

Every number traces to a file. Any figure quoted in the memo must appear in a row of a .csv in tables/ or be printed by a named script. A number that exists only in prose cannot be checked and is treated as absent.

The memo answers four questions and stops. What was run, what came out, what the ruling is, and what remains unresolved. Two pages is a limit rather than a target. Background belongs in the proposal, not in a memo.

Figures carry their own axis labels, units and sample sizes. A figure that needs the memo to be readable is not finished. Every panel showing a canopy coefficient carries the conditional-interpretation sentence in its caption from the first draft onward, so it does not have to be added later.

Sealed files stay sealed. Where a step produces point estimates before a gate decision, they go in a separate file whose checksum is recorded in the memo and which is not opened until the decision is written in the decision log.

## 2. Review outcomes

Each deliverable receives one of four rulings, recorded in the decision log.

| Ruling | Meaning |
| --- | --- |
| Accept | The step is closed. Work proceeds. |
| Accept with corrections | Substance is sound; named items are fixed before the next deliverable is submitted. |
| Return | A required element is missing or a number cannot be reproduced. The step is resubmitted. |
| Stop or reframe | The step produced evidence that a gate criterion cannot be met. |

## 3. The first delivery: D0 through D1d

These five deliverables are due together within five working days and are reviewed as one package. Gate A is not authorised until the package is accepted. No new thermal processing happens during this period.

### D0. Control boundary and frozen protocol

Day 1, morning. No figures. No results.

| Item | Content |
| --- | --- |
| Repository evidence | Branch name, tag hash of the last inherited commit, a directory listing showing the four separated output roots, and checksums.txt for every inherited file |
| protocol_v6_2.yml | Every blank filled that the free checks depend on: exact Science TCC release identifier and checksum, canopy unit convention, provisional tree and background thresholds with the separating gap, season windows, geometry sets, Stage 1 formula, predicted signs, power constants, gate thresholds. Blanks that only Gate A can fill are marked PENDING_GATE_A rather than left empty |
| decision_log_v6_2.md | Initialised with entry 1, recording the freeze |
| prior_thermal_access.md | One row per earlier Phoenix LST analysis: date, city, what was viewed, under which retired design, and why it does not determine the new coefficient |
| conformance_memo.md | One page listing what earlier versions of the proposal and guides must mirror |

Accepted when a fresh clone reproduces the structure, retired and synthetic outputs cannot write into scientific output folders, prior thermal access is disclosed in full, and no new coefficient has been opened.

Lands in the paper as the supplement methods timeline, the version-history table, and the data-availability statement.

### D1a. Demand and geometry support

Day 1 afternoon to day 2. One memo, one figure, two tables.

- d1a_pairwise.csv holds within-city correlations among exact-time VPD, air temperature, actual vapour pressure or dewpoint, local solar time, solar zenith, solar azimuth, view zenith, relative sun–sensor azimuth, and day of year. One block per city.

- d1a_condition_index.csv holds condition indices, variance inflation factors and concurvity diagnostics for the candidate interaction design matrix, per city. Pairwise correlation alone does not settle the ruling and is reported as description.

- d1a_support.png shows small multiples of VPD against solar zenith, local solar time and day of year, one row per city, with the continuously supported range shaded.

- The memo states the keep or drop ruling for the demand branch, with the numbers it rests on.

Accepted when the ruling states exactly which variation would identify the interaction, and no branch is retained because it sounds more publishable.

Lands in the paper as a supplement support matrix. It becomes a main figure panel only if RQ2 survives.

### D1b. Block-pass connectivity and representation

Days 2 to 3. One memo, two figures, one table.

d1b_connectivity.csv carries one row for each city crossed with each season window and each geometry set, so eight rows for two cities. Columns: city, season window, view-zenith set, eligible blocks, eligible passes, block-passes, median passes per block, 10th-percentile passes per block, blocks below the floor, largest-component share, spatial sectors represented, and the largest share held by a single land-use class.

- d1b_map.png shows eligible blocks per city, coloured by number of passes, with the urban core boundary drawn.

- d1b_hist.png shows the distribution of passes per block, four panels per city for the window and geometry combinations.

- The memo states the ruling and whether the one pre-authorised widening was used.

Accepted when all four combinations are reported rather than the single most favourable one, and the maps show no airport, desert-fringe or single-park domination.

Lands in the paper as the Figure 1 support panel and the Methods sample description.

### D1c. Lead-lag feasibility

Day 3. One memo, one figure, one table.

d1c_leadlag.csv reports, by city, year, season window and sensor: candidate passes, passes with a feasible matched pre-pass and post-pass observation at comparable absolute lag, the share, the number of unique optical acquisition identifiers, and the largest number of thermal passes sharing one acquisition.

- d1c_timing.png shows a histogram of pre-pass and post-pass lags in days.

- The memo states whether the temporal-specificity diagnostic stays confirmatory or is demoted to exploratory.

Accepted when the count is presented as feasibility only, with an explicit statement that the centred inherited product is not the final placebo construction.

Lands in the paper as the supplement timing histogram.

### D1d. Stage 1 precision census

Days 3 to 5. One memo, two figures, two tables, one sealed file. This is the deliverable most likely to end the project cheaply, and it receives the closest reading.

d1d_stage1_se.csv carries one row per block-pass, with no point estimates: block identifier, pass identifier, valid cell count, canopy span between the 10th and 90th percentiles, mean canopy fraction, spatially robust standard error of the slope in kelvin per 10 percentage points, leverage diagnostic, residual spatial autocorrelation, and convergence flag.

d1d_coefficients_SEALED.csv holds the point estimates. Its checksum is recorded in the memo and it is not opened until the free-check ruling is written.

d1d_n_required.csv is a grid: reliability at 0.30, 0.50 and 0.70, crossed with the observed Stage 1 standard error, crossed with the detection and equivalence criteria, giving the required connected block-pass count in each cell. The available connected count from D1b sits in its own column beside them.

- d1d_se_distribution.png shows a histogram or empirical cumulative distribution of the spatially robust standard errors, with the median and interquartile range marked.

- d1d_n_required.png plots required block-passes against σ_s, with two curves for detection and equivalence, a horizontal line at the available connected count, and one panel per reliability value.

- The memo states the ruling, plus these three cautions: the Stage 1 standard error is a measurement-error floor rather than the Stage 2 residual standard deviation; connected block-passes rather than all rows define the usable graph; and passes sharing one HLS acquisition are dependent.

Accepted when the implementation produces one slope per block-pass rather than one global slope per pass, standard errors come from spatial resampling rather than nominal cell counts, the square-root attenuation rule is used, both the detection and equivalence counts appear, and the sealed file is intact.

Lands in the paper as the methods panel for Figure 2, the supplement precision and leverage plots, and the power paragraph in Methods.

## 4. Deliverables for the remaining steps

| ID | Deliverable and required content | Lands in |
| --- | --- | --- |
| D2 | Spatial frame. Two maps, one table, geopackages. City cores and 1 km blocks with stable hashes; native-cell index; area and block-count summary by city; season-window record. | Figure 1A; Methods study area |
| D3 | Canopy, context, rainfall. Three figures, three tables, raster stack. Frozen TCC release metadata; stable-canopy mask and change-screen summary; fixed 2019–2025 median canopy; NAIP validation of 100 cells per city with canopy ranking and registration offset; antecedent rainfall table; irrigation table where records exist; CE unit-test result. | Figure 1C; Methods canopy; supplement change-screen sensitivity |
| D4 | Build G, W_tree, W_bg. Three figures, two tables, block-pass condition table. Construction schematic; maps of the three variables for one representative city-pass; optical age distribution and acquisition-reuse counts; excluded mixed fraction per block-pass; split-half and cross-sensor replicate identifiers; matched pre and post variables. | Figure 1D–1E; Methods exposure |
| D5 | Gate A. Gate A report, four figures, five tables, simulation code. Reliability by variable, method and scale; construct-validity matrix; identifying-component distributions and leverage; tree and background partial correlation and cross-error covariance; rainfall and season ruling; simulation operating characteristics reporting detection power and equivalence power separately; lead-city ruling with its numbers; signed go or stop memorandum. | Figure 1F–1H; main Table 2; supplement simulation panels |
| D6 | Gate B. Precision report, two figures, two tables, one sealed file. Observed Stage 1 standard-error distribution against the Gate A assumption; leverage; registration sensitivity; common-cell and reweighted estimability; composition tests; runtime forecast; sealed coefficient file with checksum and access log. | Supplement Gate B precision; Figure 2 draft |
| D7 | LST archive. One figure set, three tables, versioned archive. Per-mask pixel-retention table; reconciled attrition ledger with terminal categories summing to the raw catalogue; excluded-scene appendix; one QC quicklook per city-year. | Figure 2A; supplement coverage and QC |
| D8 | Block-pass tables. One table, one data dictionary, partitioned dataset. Row-count and source-image-reuse tables; missingness by variable and city; five-pass reconstruction audit; data dictionary with units and aggregation rules. | Figure 2B–2C; Methods data |
| D9 | Stage 1. Three figures, three tables. Block-pass slope tables for Models A and B; spatial uncertainty; composition tests regressing cell count, span, mean canopy, standard error and acceptance on W_tree and on W_bg; independent per-block fit comparison; rejection log. | Figure 2D–2E; Methods estimator |
| D10 | Stage 2. Four figures, four tables. Coefficients for G, W_tree and W_bg on the observed scale; joint sign-contrast test with covariance and the proportion of draws in the predicted quadrant; city-specific and pooled estimates; predicted CE at normal against −1 observed SD; measurement-error propagation; source-cluster and one-stage sensitivities; irrigation stratification; single block-mean W cancellation demonstration. | Figure 3; main Table 3; supplement cancellation panel |
| D11 | Negative controls. Three figures, three tables. Antecedent against matched future W for both populations and the joint model; rainfall control and rainfall-free-block subset; season-window contrast; background-class placebo; optical-age strata; threshold-gap sensitivity; within-pass permutation. | Figure 4A–4C |
| D12 | Demand specificity. One figure, two tables. Interaction refitted with air temperature, with air temperature plus dewpoint, with solar zenith and with day of year; blocked predictive comparison; within-city concurvity. | Figure 3E if retained, otherwise supplement |
| D13 | Night diagnostic. One figure, one table. Night model with its own baseline, tree and background terms together, and the permitted interpretation named in the caption. | Figure 4I if feasible |
| D14 | Robustness. Two figures, two tables. Load-bearing pass or fail table with the prewritten consequence for each failure; descriptive sensitivity forest plot kept separate; uncertainty budget. | Figure 4D–4G; main Table 4 |
| D15 | Second city. Two figures, two tables. City-specific estimates side by side; equal-city pooling; leave-one-city-out; confirmation that no threshold changed. | Figure 3C; Figure 4H |
| D16 | Reproduction and submission. Reproduction memo, four final figures, supplement, package. Independent reproduction of one headline estimate by a second analyst using a script that imports nothing from the main package; vocabulary search record with query strings and dates; resolved DOIs; claim-strength matrix; full reproducibility package. | Manuscript and supplement |

The identifier encodes the step, so D9 is the product of Step 9 in the Step-by-Step Guide.

## 5. How deliverables aggregate into the paper

No single step produces a manuscript figure. Each of the four figures is assembled from several deliverables, which is the reason each deliverable is stored as data and source files rather than as a finished image.

Figure 1. Exposure and identification. Panel A from D2. Panel B from D1b and D2. Panel C from D3. Panels D and E from D4. Panels F, G and H from D5. This figure is the argument that the exposure is measurable and separable, and it cannot be drawn before Gate A closes.

Figure 2. What a block-pass slope is. Panel A from D7. Panel B from D3 and D8. Panel C from D8, choosing two blocks of similar canopy amount and contrasting W_tree. Panels D and E from D9. The block pair is selected on exposure and support only, never on the slope it produces, and the selection rule is recorded in the decision log at D8.

Figure 3. Main result. Panels A to D from D10, with the city-specific panel completed at D15. Panel E from D12 and only if the demand branch survived D1a and D5.

Figure 4. Where the result holds. Panels A to C from D11. Panels D to G from D9 and D14. Panel H from D15. Panel I from D13. The irrigation stratification from D10 appears here or in Figure 3 depending on whether it changes the headline.

Main tables. Table 1 combines D2, D3, D4 and D7 into one study-design and data summary. Table 2 is the Gate A operating-characteristics table from D5. Table 3 is the Stage 2 coefficient table from D10. Table 4 is the load-bearing claim-validity matrix from D14.

Supplement. Attrition ledger from D0 and D7. View-geometry write-up from D0 and D7. Simulation operating characteristics from D5. Gate B precision from D6. Cancellation demonstration from D10. Descriptive sensitivity forest plot from D14. Vocabulary search record from D16.

## 6. Numbers the manuscript will report, and who owns them

These quantities appear in the abstract, Methods or Results and are checked against their source deliverable. Each is owned by one deliverable, so a later change to any of them requires a decision-log entry.

| Quantity | Owner |
| --- | --- |
| Blocks, passes and connected block-passes per city | D1b, updated at D8 |
| Median and 90th-percentile optical age | D4 |
| Number of thermal passes sharing one optical acquisition | D4 |
| Excluded mixed-pixel fraction | D4 |
| Reliability of W_tree and W_bg by method | D5 |
| Standard deviation of each identifying component | D5 |
| Detection power and equivalence power | D5 |
| Median Stage 1 standard error in kelvin per 10 percentage points | D1d, confirmed at D6 and D9 |
| θ_g, θ_wt, θ_wb with intervals on the observed scale | D10 |
| Sign-contrast statistic and the proportion of draws in the predicted quadrant | D10 |
| City-specific estimates and the leave-one-city-out result | D15 |
| Independent reproduction tolerance | D16 |

## 7. Review checklist

Applied to every deliverable before it is accepted.

- The folder follows the naming and packaging convention, and the commit hash resolves.

- Every number in the memo appears in a table or is printed by a named script.

- Figures are legible without the memo and carry units and sample sizes.

- Where a coefficient exists at this stage, it is in a sealed file whose checksum is recorded.

- The ruling is stated in one sentence and is supported by the numbers above it, not by a general impression.

- Anything unresolved is named rather than omitted.

- No threshold, window, class definition or model term changed since the last accepted deliverable without a decision-log entry.

- Terminology follows the lock: optical condition anomaly, not moisture, health or stress.

## 8. Sequencing summary

| Package | Deliverables | Due | Gate |
| --- | --- | --- | --- |
| 1. Freeze and free checks | D0, D1a, D1b, D1c, D1d | Working day 5 | Authorisation to begin Gate A |
| 2. Exposure and Gate A | D2, D3, D4, D5 | End of week 4 | Gate A go or stop; lead-city, season and background rulings |
| 3. Thermal pilot | D6 | End of month 3 | Gate B go or stop |
| 4. Lead-city analysis | D7, D8, D9, D10 | End of month 5 | Single-city draft reviewed |
| 5. Controls | D11, D12, D13 | End of month 6 | Claim strength assessed |
| 6. Second city and robustness | D14, D15 | End of month 8 | City set frozen |
| 7. Submission | D16 | End of month 9 | Manuscript submitted |

Packages are reviewed as units. A package is not accepted while any deliverable inside it is outstanding, because the rulings inside a package depend on each other.